## Summary
Iteration | Functionality | Planned Start Date | Planned End Date | Actual Start Date | Actual End Date | SM | Mitigation Plan/ Remarks | No. Buffer Days left
1 | Diagrams and Rotation Plan | 2015-09-14 | 2015-09-21 | 2015-09-14 | 2015-09-21 | 1 | - | 3
2 | Login, Bootstrap, Location Deletion | 2015-09-21 | 2015-10-01 | 2015-09-22 | 2015-10-05 | 0.73 | Problem We faced bootstrap issue on OpenShift which delays the iteration. Mitigation 1. Consulted Prof. 2. Task one pair to continue test and debugging for Bootstrap function in Iteration 3 (This is to ensure that the other 2 pairs have tasks to do). Problem We start our tasks later than what we have planned. Because coding pairs were unable to code on the assigned date. Mitigation For following Iterations, the pairs will be asked for their available coding hours and days. Based on this information and coding ability of each pair, PM will assign critical tasks to each pair accordingly to avoid delay and readjust schedule to be more realistic. Problem After rescheduling: Iteration 3 - initial period is 02 Oct - 12 Oct - readjusted period is 06 Oct - 20 Oct Therefore Iteration 3 is ended 8 days later than expected. Iteration 4 and 5 will therefore start later. This means that we have negative buffer days to UAT (based on initial schedule) if we were to complete all the functions. Mitigation We proposed to drop "Social Activeness Report" function. | 0
3 | Basic App Report | 2015-10-06 | 2015-10-20 | 2015-10-06 | 2015-10-20 | 1 |  | 0
4 | Top-K | 2015-10-21 | 2015-10-27 | 2015-10-21 | 2015-10-27 | 0.86 | "Social Activeness Report" function is dropped. Problem Functional requirement has changed but we have 0 buffer day. Mitigation We had to increase workload for Iteration 4. Changes in boostrap and location delete was done in Iteration 4, while demographics will be done in Iteration 5. Test cases are to be updated to include the change in requirement. In Iteration 5, PM will strategically pair up the coders that is best suited for each task and plan breakdown of testing and debugging task of all functions to ensure that the existing functions are functional with the new changes. | 0
5 | Heatmap, Overuse Report | 2015-10-29 | 2015-10-07 | 2015-10-29 | 2015-11-08 | 1.1 | The iteration actual end date is 7 -Nov-15 however we didn't record UAT task in schedule so pplog system SM calculation is different | 0
6 | Debugging and presentation | 2015-11-08 | 2015-11-13 | 2015-11-08 | 2015-11-13 | 1 |  | 0